## Sheet1
TASK SHEET
Project Ref. No 1 |  | Project Title | Activity Plan Prepared By | Date of Preparation of Activity Plan
Sr. No | Task |  |  | Start Date | End Date | Actual Days | Member’s name | Status
CRS document
1 | Introduction | WorkToWorker | Trinh Cong Thanh | 09/23/2013 | 09/26/2013 | 3 | All of Team | FINISH
2 | Existing Scenario | WorkToWorker | Trinh Cong Thanh | 09/23/2013 | 09/26/2013 | 3 | All of Team | FINISH
3 | Customer Requirement Specification | WorkToWorker | Trinh Cong Thanh | 09/23/2013 | 09/26/2013 | 3 | All of Team | FINISH
4 | Functional Requirement Specification | WorkToWorker | Trinh Cong Thanh | 09/23/2013 | 09/26/2013 | 3 | All of Team | FINISH
5 | System Requirements | WorkToWorker | Trinh Cong Thanh | 09/23/2013 | 09/26/2013 | 3 | All of Team | FINISH
6 | Development Software | WorkToWorker | Trinh Cong Thanh | 09/23/2013 | 09/26/2013 | 3 | All of Team | FINISH
Use Case and Sequence Diagrams
Customer
7 | Register Custommer | WorkToWorker |  | 09/26/2013 |  |  | Trinh Cong Thanh
8 | Login | WorkToWorker |  | 09/26/2013 |  |  | Trinh Cong Thanh
9 | Update profile | WorkToWorker |  | 09/26/2013 |  |  | Trinh Cong Thanh
10 | Add worker to group | WorkToWorker |  | 09/26/2013 |  |  | Trinh Cong Thanh
11 | Manage Group Worker | WorkToWorker |  | 09/26/2013 |  |  | Trinh Cong Thanh
12 | View Custommer, Woker, Genaral public | WorkToWorker |  | 09/26/2013 |  |  | Trinh Cong Thanh
13 | Search General Public and Woker, Custommer | WorkToWorker |  | 09/26/2013 |  |  | Trinh Cong Thanh
14 | Create and Import Work caledar | WorkToWorker |  | 09/26/2013 |  |  | Trinh Cong Thanh
15 | Feedback and rating for worker | WorkToWorker |  | 09/26/2013 |  |  | Trinh Cong Thanh
16 | Add new work | WorkToWorker |  | 09/26/2014 |  |  | Trinh Cong Thanh
General Public
17 | Register General Public | WorkToWorker |  | 09/26/2013 |  |  | Hong Lam Son
18 | Login | WorkToWorker |  | 09/26/2013 |  |  | Hong Lam Son
19 | Update profile | WorkToWorker |  | 09/26/2013 |  |  | Hong Lam Son
20 | Select Customer or worker | WorkToWorker |  | 09/26/2013 |  |  | Hong Lam Son
21 | View General Publict, Customer,Worker | WorkToWorker |  | 09/26/2013 |  |  | Hong Lam Son
22 | Search Customer and Woker,General Public | WorkToWorker |  | 09/26/2013 |  |  | Hong Lam Son
23 | Create and Import Work caledar | WorkToWorker |  | 09/26/2013 |  |  | Hong Lam Son
24 | Add new work | WorkToWorker |  | 09/26/2014 |  |  | Hong Lam Son
25 | Feedback and rating for worker | WorkToWorker |  | 09/26/2013 |  |  | Hong Lam Son
Worker
26 | Register Worker | WorkToWorker |  | 09/26/2013 |  |  | Nguyen Chi Tan
27 | Login | WorkToWorker |  | 09/26/2013 |  |  | Nguyen Chi Tan
28 | Update profile | WorkToWorker |  | 09/26/2013 |  |  | Nguyen Chi Tan
29 | View Worker, Customer, Group of Customer, General public | WorkToWorker |  | 09/26/2013 |  |  | Nguyen Chi Tan
30 | Search Worker, Customer, Group of Customer, General public | WorkToWorker |  | 09/26/2013 |  |  | Nguyen Chi Tan
31 | View and Export to Work caledar | WorkToWorker |  | 09/26/2013 |  |  | Nguyen Chi Tan
Administrator
32 | Login | WorkToWorker |  | 09/26/2013 |  |  | Phan Trong Nhan
33 | Logout | WorkToWorker |  | 09/26/2013 |  |  | Phan Trong Nhan
34 | Manage Customer | WorkToWorker |  | 09/26/2013 |  |  | Phan Trong Nhan
35 | Manage Worker | WorkToWorker |  | 09/26/2013 |  |  | Phan Trong Nhan
36 | Manage General public | WorkToWorker |  | 09/26/2013 |  |  | Phan Trong Nhan
37 | Report | WorkToWorker |  | 09/26/2013
ERD
38 | Conceptual | WorkToWorker
39 | Logical | WorkToWorker
40 | Table | WorkToWorker
41 | Database Relationship | WorkToWorker
42 | Table Definition | WorkToWorker