## Sheet1
TASK SHEET
Project Ref. No 1 |  | Project Title | Activity Plan Prepared By | Date of Preparation of Activity Plan
Sr. No | Task |  |  | Start Date | End Date | Actual Days | Member’s name | Status
CRS document
1 | Introduction | WorkToWorker | Trinh Cong Thanh | 09/23/2013 | 09/26/2013 | 3 | All of Team | FINISH
2 | Existing Scenario | WorkToWorker | Trinh Cong Thanh | 09/23/2013 | 09/26/2013 | 3 | All of Team | FINISH
3 | Customer Requirement Specification | WorkToWorker | Trinh Cong Thanh | 09/23/2013 | 09/26/2013 | 3 | All of Team | FINISH
4 | Functional Requirement Specification | WorkToWorker | Trinh Cong Thanh | 09/23/2013 | 09/26/2013 | 3 | All of Team | FINISH
5 | System Requirements | WorkToWorker | Trinh Cong Thanh | 09/23/2013 | 09/26/2013 | 3 | All of Team | FINISH
6 | Development Software | WorkToWorker | Trinh Cong Thanh | 09/23/2013 | 09/26/2013 | 3 | All of Team | FINISH
Use Case and Sequence Diagrams
7 | Customer
8 | Register Custommer | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Trinh Cong Thanh
9 | Login | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Trinh Cong Thanh
10 | Update profile | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Trinh Cong Thanh
11 | Add worker to group | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Trinh Cong Thanh
12 | Manage Group Worker | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Trinh Cong Thanh
13 | View Custommer, Woker, Genaral public | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Trinh Cong Thanh
14 | Search General Public and Woker, Custommer | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Trinh Cong Thanh
15 | Create and Import Work caledar | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Trinh Cong Thanh
16 | Feedback and rating for worker | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Trinh Cong Thanh
17 | General Public
18 | Register General Public | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Hong Lam Son
19 | Login | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Hong Lam Son
20 | Update profile | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Hong Lam Son
21 | Select Customer or worker | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Hong Lam Son
22 | View General Publict, Customer,Worker | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Hong Lam Son
23 | Search Customer and Woker,General Public | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Hong Lam Son
24 | Create and Import Work caledar | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Hong Lam Son
25 | Add new work | WorkToWorker | Trinh Cong Thanh | 09/26/2014 | 2013-10-01 | 4 | Hong Lam Son
26 | Feedback and rating for worker | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Hong Lam Son
27 | Worker
28 | Register Worker | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Nguyen Chi Tan
29 | Login | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Nguyen Chi Tan
30 | Update profile | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Nguyen Chi Tan
31 | View Worker, Customer, Group of Customer, General public | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Nguyen Chi Tan
32 | Search Worker, Customer, Group of Customer, General public | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Nguyen Chi Tan
33 | View and Export to Work caledar | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Nguyen Chi Tan
34 | Administrator
35 | Login | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Phan Trong Nhan
36 | Logout | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Phan Trong Nhan
37 | Manage Customer | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Phan Trong Nhan
38 | Manage Worker | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Phan Trong Nhan
39 | Manage General public | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Phan Trong Nhan
40 | Report | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Phan Trong Nhan
41 | Manage Post | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Phan Trong Nhan
42 | Manage Box | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | Phan Trong Nhan
ERD
43 | Conceptual | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | All of Team
44 | Logical | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | All of Team
45 | Table | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | All of Team
46 | Database Relationship | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | All of Team
47 | Table Definition | WorkToWorker | Trinh Cong Thanh | 09/26/2013 | 2013-10-01 | 4 | All of Team
GUI
48 | index.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Trinh Cong Thanh
49 | login.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Trinh Cong Thanh
50 | loginadmin.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Trinh Cong Thanh
51 | registerWorker.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Trinh Cong Thanh
52 | registerHire.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Trinh Cong Thanh
53 | Administrator
54 | index.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Phan Trong Nhan
55 | manageAccount.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Trinh Cong Thanh
56 | viewAlluser.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Trinh Cong Thanh
57 | deleteUser.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Trinh Cong Thanh
58 | updateinformationUser.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Trinh Cong Thanh
59 | manageForum.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Phan Trong Nhan
60 | manage Post.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Phan Trong Nhan
61 | deleteToppic | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Phan Trong Nhan
62 | deletePost.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Phan Trong Nhan
63 | manageBox.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Phan Trong Nhan
64 | report | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Phan Trong Nhan
65 | Forum
66 | index.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Phan Trong Nhan
67 | topix.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Phan Trong Nhan
68 | post.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Phan Trong Nhan
69 | createPost.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Phan Trong Nhan
70 | Edit post.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Phan Trong Nhan
71 | createPost.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Phan Trong Nhan
72 | Edit post.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Phan Trong Nhan
73 | Worker
74 | index.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Nguyen Chi Tan
75 | manageAccount.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Nguyen Chi Tan
76 | view.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Nguyen Chi Tan
77 | updateProfile.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Nguyen Chi Tan
78 | changePassword.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Nguyen Chi Tan
79 | otherWoker.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Nguyen Chi Tan
80 | recruiter.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Nguyen Chi Tan
81 | exportCalendarWork. | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Nguyen Chi Tan
82 | addcv.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Nguyen Chi Tan
83 | work
84 | index.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Hong Lam Son
85 | addWork.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Hong Lam Son
86 | editwork.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Hong Lam Son
87 | rating.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Hong Lam Son
88 | feedback.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Hong Lam Son
89 | addGroup.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Hong Lam Son
90 | editGruop.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Hong Lam Son
91 | addWorkDaily.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Hong Lam Son
92 | EditWorkDaily.xhtml | WorkToWorker | Trinh Cong Thanh | 2013-03-10 | 10/23/2013 | 4 | Hong Lam Son